## Sheet1
Task | When | Details | Who does… | Status
Name your event | 3-4 months before | Look at past events for ideas, no references to racing. Get approval from the HPDE Chair | Event Chair
Write a short article describing your event for use in HighGear, e-Blasts, on the RMR PCA web site, and on Motorsportsreg.com (send it to your registrar). | 3-4 months before | HighGear articles are due by the 15th of the month prior to the publication month The first e-Blast should be sent out approximately 8 weeks before the event. The registration site should be available no later than 1 month prior to the event (registration opens 1 month before the event at 9:11 AM MT. Look at past articles/ads for inspiration. The HPDE Chair can help here | Event Chair
Check to be sure your event is on the RMR PCA event calendar | 3 months before | Work with the RMR PCA webmaster to post the event | Event Chair
Connect w/ the event CDI(s) (and/or CDI Chair if the event CDI hasn't been assigned) to learn of any unique elements that will be part of your event (different schedules, alternate track layouts, etc.) | 3 months before |  | Event Chair
Find a photographer(s) for the event. | 2 months before | Generally Mike Pappas and/or Scott Pedram | Event Chair
Write a second newsletter article/republish the original article | 2 months before | See above, this revised article can also be sent out as an e-Blast | Event Chair
Social media posts | 2 months before | Post about your event on the RMR's Facebook page | Event Chair
Notify the HPR Café if you paln to have a Saturday night dinner. Details on working with the HPR Café are in the event chair manual | 2 months before | An initial heads up is all that is needed at this time | Event Chair
Contact (or Stay in Contact With) Standing Committee Chairs In general, the Chairs of these committees will insure that the functions of their committee will be executed for your event without the need for you to do anything. However, you should contact the Chair early in your planning and again the week before the event to be sure everything is on track. | 6-8 weeks before | CDI, Equipment, Registrar, Safety (request insurance be issued), Tech Inspection, Grid, Control, Photographer | Event Chair
Confirm PCA Insurance has been ordered for pre-tech (DEs) and event. Arrange to get Certificate of Insurance (COI) from PCA through Insurance Coordinator. Note: we must also send the COI to HPR. The insurance chair will do this as a part of their process. | 8 weeks before | Contact the Insurance Coordinator to obtain this | Event Chair
Think about contacting other car clubs with information about your event. | 6-8 weeks before | AMR, BMW, Mini, etc. Only needed if you are concerned about registration numbers (typically not a problem) | Event Chair
Contact 1st VP about additional E-Blasts. | 4 and 2 weeks before | Exact timing will depend on registration numbers. At the minimum send out a reminder when registration opens
Contact Standing Committee Chairs and volunteer coordinators (details below) to confirm all is in order | 2 Weeks prior to Your Event | Equipment | Event Chair
General check-in |  | Chief Driving Instructors | Event Chair
General check-in |  | Registrar | Event Chair
Confirm that PCA insurance has been issued for pre-tech. Arrange to get a copy of the insurance certificate. |  | Safety | Event Chair
Ensure no changes to pre-tech locations, ensure that there people assigned for tech inspections at the track |  | Tech Inspection - Pre-tech and at Event | Event Chair
Ensure Control is sufficiently staffed |  | Control | Event Chair
Ensure Grid is sufficiently staffed |  | Grid | Event Chair
Find an observer, typically someone from another region |  | Observer - typically Mike Childs | Event Chair
Finalize details around water, ice, lunches, and dinner |  | Provide HPR Café the final #s for water, ice, volunteer lunches, Saturday dinner. They have a form for this that you can obtain from the HPDE Chair | Event Chair
Confirm one or more photographers will be at the event |  | Photographer | Event Chair
Find volunteers to lead the lunchtime charity drives (needs to be an instructor or, at the very least, a blue solo driver). One lead, one sweep |  | Typically Rex and Grant Kennedy do this
Registration closes | Starting approximately one week before event | Registration will close on Monday at 11:59 pm . | Event Registrar
Maintain contact! |  | Stay in contact with the Registrar, CDIs, and all your volunteers to make sure everything is ready. | Event Chair
Purchase beverages and snacks for Beer:30 | It's up to you | You, or a desginated volunteer, is responsible for getting these items to the event on each event day | Event Chair
Friday Afternoon | Friday afternoon | Assist equipment chairs as needed with their duties | Event Chair
Post insurance certificates and event schedule |  | Post insurance certificates in at least 2 places, post schedule in the same locations | Event Chair
Offer to help others as needed |  | Equipment, registrar, CDIs, etc. | Event Chair
Ensure tech inspection people are ready to go | Each event day by 7:30 AM |  | Tech Inspection
Ensure registrar is ready to go |  |  | Registrar and Event Chair
Ice down waters in the pavilllion, check and restock regularly |  |  | Event Chair
Drivers's meeting | Each event day at 8:00 AM | Welcome Participants, Thank event workers, mention charity and noon-time track tours… 5 minute limit!! | Event Chair
Ice down beers and other beverages, set out any snacks | Each event day by ~ 3:00 PM |  | Event Chair
Beer:30 | Each event day when track goes cold | Cheers to a successful day! | Event Chair
Clean up | After Beer:30 ends | Clean up | Event and Equipment Chairs
Beverage and snack inventory | End of day on Sunday | Prepare a simple inventory (take pictures) of beverages (and other items such as snacks, cups, and tableware) left over for next event. Pass to next chair. | Event Chair
Beer:30 clean up |  | Clean up Refreshments and Trash | Event and Equipment Chairs
Track clean up |  | Assist Equipment Chair with clean up as needed | Event and Equipment Chairs
Observer's report | Within one week | Check to be sure the Observer’s Report has been filed on PCA National website. (https://web.pca.org/?event=observersReports.observerReportFormMain&m=OwMhExBYmdoLtHLV%2FJa167%2BX7FNUEsyTigoO2omdUo8%3D) | Event Chair
Post event report |  | Check to be sure the Observer’s Report has been filed on PCA National website. (https://web.pca.org/?event=observersReports.observerReportFormMain&m=OwMhExBYmdoLtHLV%2FJa167%2BX7FNUEsyTigoO2omdUo8%3D) | Event Chair
Expense reports |  | Submit all expense reports as soon as possible after event. | Event Chair with Treasurer
Final article |  | Send your final article with lots of pictures to newsletter editor. | Event Chair